Problem statement & SMART Objectives:

Employees are wasting 30 minutes daily searching for parking, causing frustration and lost work time. Since there is no budget for new sensors, the company needs a software solution that uses existing low-resolution cameras and gate data to track and display available spots in real-time.

SMART Objectives:

95% Tracking Accuracy:Use existing entry/exit cameras to count cars with 95% precision within the first month.

Real-Time Dashboard: Launch a simple mobile-friendly webpage that updates vacancy counts every 30 seconds.

Gate Sync: Connect the software to the current barrier gates to automatically stop entry when the lot is full.

Legacy Hardware Optimization: Ensure the software correctly identifies cars even on low-resolution footage within 2 weeks of testing.

Budget Control: Complete the entire planning and pilot setup without exceeding the $5,000 limit.

Scope Statement(Inclusion & Exclusions):

Inclusion:

Entry/Exit Counting : Software that counts cars as they pass through the existing camera views.

Digital Counter : That tracks how many cars are currently in the lot.

Availability Dashboard : A simple webpage for employees showing the number of free spots.

Gate Control : Automated Open/Close signals to the barrier gates based on lot capacity.

Low-Resolution Compatibility : Software filters designed to work specifically with your grainy, older video feeds.

Exclusions:

Specific Spot Tracking : We won't know which exact stall is taken, only the total count.

Pre-booking : No system for reserving spots in advance.

Payments : No billing or fine collection features.

Live Video Feeds : Employees won't see a video stream.

Plate Recognition  : The current cameras are too low-resolution to read license plates reliably.

Feasibility &Cost Analysis Report:

Feasibility:

Virtual Tripwire: We won't try to recognize cars. Instead, the software will detect movement crossing a digital line at the entry/exit points.

Noise Reduction:Low resolution graininess will be filtered using OpenCV (an open-source tool) to focus on large shapes rather than fine details.

Gate Logic: We will cross-reference camera motion with the gate opening signal to double check every car, ensuring high accuracy despite poor image quality.

Cost Analysis:

Item                                                     Purpose                                                  Cost

CV Specialist         40 hours of expert coding to set up the tripwire logic             $3,000

Local Mini-PC       Runs the software onsite to avoid expensive cloud fees            $700

Cloud API/Host     Hosts the simple Available Spots webpage for employees        $300

Testing/Resource   Covers trial runs and hardware-to-gate wiring tests                   $500

Buffer Fund           Emergency fix for any legacy hardware issues  		           $500

Work Breakdown Structure & Schedule:

2-Week Planning Schedule:

DAY 1-3: Site Audit

- Check if old cameras can see cars and  Inspect camera angles, and check gate wiring.

DAY 4-7: Tech Design

- Specialist selects the specific CV model and creates the Virtual Tripwire logic.

DAY 8-10:Final Costing

- Get exact prices for the Min-PC(Low-End PC)  and the developer’s time and confirm API trial time.

DAY 11-14: Fianl Report

- Create the presentation and dashboard mockups for management.

Work Breakdown Structure (WBS)

1. Site Assessment (Hardware)

Camera Check:Verify if the Entry/Exit  views are clear enough to see a car-sized object.

Gate Interface:Identify the Open/Close trigger wires on the existing barrier gates.

2. Software Logic (The "Brain")

Algorithm Selection:Choose a lightweight tool (like OpenCV) that works on low-res video.

Zone Counting Setup:Define the digital "In" and "Out" lines on the camera feed.

3. User Interface (The Dashboard)

Web Mockup: Design a simple green/red "Spots Available" screen for employees.Access Point:Create a QR code plan for employees to quickly open the link.

4. Project Management

Resource Sourcing: Find and vet the CV Specialist freelancer.

Final Pitch: Assemble the problem statement, budget, and feasibility into one report.

Key Milestones

1. Day 3: Confirmation that existing cameras can see cars (no new cameras needed).

2. Day 7: Software logic approved for low-resolution processing.

3. Day 14:Presentation to Management for Project Approval.

Initial Risk Register:

Blurry Videos: Cameras are too old to see car details.

Gate Connection: Software can't talk to the old mechanical gates.

Wi-Fi Lag: Slow internet stops the dashboard from updating

### Final Project Summary

- Problem: 30-minute daily time loss for employees.

- Solution: Use existing cameras as "digital counters" to show live spot availability.

- Budget: $5,000 (Strictly focused on software and one Mini-PC).

- Deadline: Plan finished and ready for approval in 14 days.